## All
Source URL: | (combined - see individual tabs for source URLs)
PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description | Team
21003 | Run newly created FR215 check with existing result validation script | 36032 | Task | Run newly created FR215 check with existing result validation script | John Streckfuss II | To Do |  | 2 |  | QA / Testing |  |  | FPSO
31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch | FPSO
34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11 |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14 |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing |  |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14 |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14 |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14 |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02 |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04 |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions() | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed. | FPSO
34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
34791 | Complete Transverse Detail Logging Framework | [11 empty] | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing |  |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing |  |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing |  |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | FPSO
35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35320 | TBHD result verification - Panamax Manual Fr60 | 36036 | Task | TBHD result verification - Panamax Manual Fr60 | John Streckfuss II | In Progress |  | 4 | 3 | Development |  |  | FPSO
35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf. | FPSO
35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | FPSO
35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | FPSO
35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development |  |  | FPSO
35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development |  |  | FPSO
35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing |  |  | FPSO
35650 | Create RuleSet for FPSO ReassessedScantling | [11 empty] | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData() | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | FPSO
35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14 |  | FPSO
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | FPSO
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14 |  | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()()) | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified. | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08 |  | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11 |  | FPSO
35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke | FPSO
35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | In Progress |  | 4 | 2 | Development |  | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts | FPSO
35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | FPSO
35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | FPSO
35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10 |  | FPSO
35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10 |  | FPSO
35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression | FPSO
35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression | FPSO
35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results | FPSO
35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11 |  | FPSO
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36264 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. Current State Documentation | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36265 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as deisgnated by the lead developer's plans. - Planned Changes Document - Verification Document | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36266 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | FPSO
35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36267 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. - Current State Documentation - End State Document | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36268 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as designated by the lead developer's plans. - Planned Changes Document - Verification Document | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36269 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | FPSO
35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63 | FPSO
35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 3 | Development |  |  | FPSO
35906 | Manual BC Slanted BHD Fr245 - Plate | 36026 | Task | Manual BC Slanted BHD Fr245 - Plate | John Streckfuss II | To Do |  | 8 |  | Development |  |  | FPSO
35907 | Manual BC Slanted BHD Fr245 - stiffener | 36030 | Task | Manual BC Slanted BHD Fr245 - stiffener | John Streckfuss II | To Do |  | 6 |  | Development |  |  | FPSO
35908 | Manual BC Slanted BHD Fr245 - EPP and result check | [11 empty] | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36341 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 3 | Albert Posthauer | To Do |  | 16 | 0 | QA / Testing |  | Batch 3 - fix each one and make sure it runs | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch. | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | In Progress |  | 4 |  | Development |  |  | FPSO
35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09 |  | FPSO
35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09 |  | FPSO
35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing |  |  | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite: | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects: | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes: | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier: | FPSO
36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14 |  | FPSO
36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04 |  | FPSO
36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02 |  | FPSO
36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change | FPSO
36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15 |  | FPSO
36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab | [11 empty] | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36388 | Task | Fix 2 script issues with comments run | Albert Posthauer | To Do |  | 2 |  | Development |  | Fix these from run on 9/11/26 Gap_In_The_Section_Type_28920 Input_Property_For_TBHD_Girders_Webs_28929 | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04 |  | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04 |  | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar, | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors: | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10 |  | FPSO
36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10 |  | FPSO
36377 | Draw Label in Side Frame | [11 empty] | FPSO
36378 | Draw Label in Cross Deck | [11 empty] | FPSO
36379 | Draw Label In Side Frame | [11 empty] | FPSO
36380 | GraphicTank2D Factory Refactor | 36410 | Task | spec refinement | Timothy Luna | To Do |  | 2 |  | Requirement Study |  |  | FPSO
36386 | NDepend Safety Issue - ND3106:SealMethodsThatSatisfyNonPublicInterfaces | [11 empty] | FPSO
36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these: | FPSO
36437 | Fix NDepend violation: Avoid Namespaces Mutually Dependent — HorizontalStringerBracketDimensionGeometryResolver | [11 empty] | FPSO
21003 | Run newly created FR215 check with existing result validation script | 36032 | Task | Run newly created FR215 check with existing result validation script | John Streckfuss II | To Do |  | 2 |  | QA / Testing |  |  | Foundation
31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch | Foundation
34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11 |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14 |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing |  |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14 |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14 |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14 |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02 |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04 |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions() | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed. | Foundation
34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
34791 | Complete Transverse Detail Logging Framework | [11 empty] | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing |  |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing |  |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing |  |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | Foundation
35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35320 | TBHD result verification - Panamax Manual Fr60 | 36036 | Task | TBHD result verification - Panamax Manual Fr60 | John Streckfuss II | In Progress |  | 4 | 3 | Development |  |  | Foundation
35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf. | Foundation
35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | Foundation
35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | Foundation
35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development |  |  | Foundation
35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development |  |  | Foundation
35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing |  |  | Foundation
35650 | Create RuleSet for FPSO ReassessedScantling | [11 empty] | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData() | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | Foundation
35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14 |  | Foundation
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | Foundation
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14 |  | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()()) | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified. | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08 |  | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11 |  | Foundation
35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke | Foundation
35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | In Progress |  | 4 | 2 | Development |  | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts | Foundation
35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | Foundation
35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | Foundation
35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10 |  | Foundation
35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10 |  | Foundation
35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression | Foundation
35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression | Foundation
35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results | Foundation
35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11 |  | Foundation
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36264 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. Current State Documentation | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36265 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as deisgnated by the lead developer's plans. - Planned Changes Document - Verification Document | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36266 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | Foundation
35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36267 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. - Current State Documentation - End State Document | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36268 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as designated by the lead developer's plans. - Planned Changes Document - Verification Document | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36269 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | Foundation
35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63 | Foundation
35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 3 | Development |  |  | Foundation
35906 | Manual BC Slanted BHD Fr245 - Plate | 36026 | Task | Manual BC Slanted BHD Fr245 - Plate | John Streckfuss II | To Do |  | 8 |  | Development |  |  | Foundation
35907 | Manual BC Slanted BHD Fr245 - stiffener | 36030 | Task | Manual BC Slanted BHD Fr245 - stiffener | John Streckfuss II | To Do |  | 6 |  | Development |  |  | Foundation
35908 | Manual BC Slanted BHD Fr245 - EPP and result check | [11 empty] | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36341 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 3 | Albert Posthauer | To Do |  | 16 | 0 | QA / Testing |  | Batch 3 - fix each one and make sure it runs | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch. | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | In Progress |  | 4 |  | Development |  |  | Foundation
35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09 |  | Foundation
35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09 |  | Foundation
35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing |  |  | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite: | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects: | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes: | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier: | Foundation
36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14 |  | Foundation
36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04 |  | Foundation
36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02 |  | Foundation
36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change | Foundation
36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15 |  | Foundation
36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab | [11 empty] | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36388 | Task | Fix 2 script issues with comments run | Albert Posthauer | To Do |  | 2 |  | Development |  | Fix these from run on 9/11/26 Gap_In_The_Section_Type_28920 Input_Property_For_TBHD_Girders_Webs_28929 | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04 |  | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04 |  | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar, | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors: | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10 |  | Foundation
36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10 |  | Foundation
36377 | Draw Label in Side Frame | [11 empty] | Foundation
36378 | Draw Label in Cross Deck | [11 empty] | Foundation
36379 | Draw Label In Side Frame | [11 empty] | Foundation
36380 | GraphicTank2D Factory Refactor | 36410 | Task | spec refinement | Timothy Luna | To Do |  | 2 |  | Requirement Study |  |  | Foundation
36386 | NDepend Safety Issue - ND3106:SealMethodsThatSatisfyNonPublicInterfaces | [11 empty] | Foundation
36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these: | Foundation
36437 | Fix NDepend violation: Avoid Namespaces Mutually Dependent — HorizontalStringerBracketDimensionGeometryResolver | [11 empty] | Foundation
35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | [11 empty] | CSR

## FPSO
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_sprints/backlog/Unified%20FPSO/Next-Gen-Eng-Apps/Develop/Sprint%20103
PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description | Team
21003 | Run newly created FR215 check with existing result validation script | 36032 | Task | Run newly created FR215 check with existing result validation script | John Streckfuss II | To Do |  | 2 |  | QA / Testing |  |  | FPSO
31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch | FPSO
34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11 |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14 |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing |  |  | FPSO
34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14 |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14 |  | FPSO
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14 |  | FPSO
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02 |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04 |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development |  |  | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions() | FPSO
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed. | FPSO
34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
34791 | Complete Transverse Detail Logging Framework | [11 empty] | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing |  |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14 |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing |  |  | FPSO
35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03 |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing |  |  | FPSO
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | FPSO
35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35320 | TBHD result verification - Panamax Manual Fr60 | 36036 | Task | TBHD result verification - Panamax Manual Fr60 | John Streckfuss II | In Progress |  | 4 | 3 | Development |  |  | FPSO
35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf. | FPSO
35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | FPSO
35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | FPSO
35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development |  |  | FPSO
35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development |  |  | FPSO
35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing |  |  | FPSO
35650 | Create RuleSet for FPSO ReassessedScantling | [11 empty] | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData() | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09 |  | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list | FPSO
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | FPSO
35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14 |  | FPSO
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | FPSO
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14 |  | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()()) | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified. | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08 |  | FPSO
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11 |  | FPSO
35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke | FPSO
35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | In Progress |  | 4 | 2 | Development |  | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts | FPSO
35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01 |  | FPSO
35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | FPSO
35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | FPSO
35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03 |  | FPSO
35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10 |  | FPSO
35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10 |  | FPSO
35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression | FPSO
35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression | FPSO
35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results | FPSO
35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11 |  | FPSO
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36264 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. Current State Documentation | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36265 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as deisgnated by the lead developer's plans. - Planned Changes Document - Verification Document | FPSO
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36266 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | FPSO
35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36267 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. - Current State Documentation - End State Document | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36268 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as designated by the lead developer's plans. - Planned Changes Document - Verification Document | FPSO
35903 | CorrugatedBHD Settings - Color Visitors | 36269 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | FPSO
35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63 | FPSO
35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 3 | Development |  |  | FPSO
35906 | Manual BC Slanted BHD Fr245 - Plate | 36026 | Task | Manual BC Slanted BHD Fr245 - Plate | John Streckfuss II | To Do |  | 8 |  | Development |  |  | FPSO
35907 | Manual BC Slanted BHD Fr245 - stiffener | 36030 | Task | Manual BC Slanted BHD Fr245 - stiffener | John Streckfuss II | To Do |  | 6 |  | Development |  |  | FPSO
35908 | Manual BC Slanted BHD Fr245 - EPP and result check | [11 empty] | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run | FPSO
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36341 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 3 | Albert Posthauer | To Do |  | 16 | 0 | QA / Testing |  | Batch 3 - fix each one and make sure it runs | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15 |  | FPSO
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch. | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08 |  | FPSO
35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15 |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | FPSO
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | In Progress |  | 4 |  | Development |  |  | FPSO
35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09 |  | FPSO
35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09 |  | FPSO
35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing |  |  | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite: | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects: | FPSO
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes: | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos | FPSO
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier: | FPSO
36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14 |  | FPSO
36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07 |  | FPSO
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04 |  | FPSO
36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02 |  | FPSO
36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change | FPSO
36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15 |  | FPSO
36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab | [11 empty] | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | FPSO
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36388 | Task | Fix 2 script issues with comments run | Albert Posthauer | To Do |  | 2 |  | Development |  | Fix these from run on 9/11/26 Gap_In_The_Section_Type_28920 Input_Property_For_TBHD_Girders_Webs_28929 | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04 |  | FPSO
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04 |  | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar, | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors: | FPSO
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10 |  | FPSO
36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10 |  | FPSO
36377 | Draw Label in Side Frame | [11 empty] | FPSO
36378 | Draw Label in Cross Deck | [11 empty] | FPSO
36379 | Draw Label In Side Frame | [11 empty] | FPSO
36380 | GraphicTank2D Factory Refactor | 36410 | Task | spec refinement | Timothy Luna | To Do |  | 2 |  | Requirement Study |  |  | FPSO
36386 | NDepend Safety Issue - ND3106:SealMethodsThatSatisfyNonPublicInterfaces | [11 empty] | FPSO
36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these: | FPSO
36437 | Fix NDepend violation: Avoid Namespaces Mutually Dependent — HorizontalStringerBracketDimensionGeometryResolver | [11 empty] | FPSO

## Foundation
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_sprints/backlog/Unified%20Foundation/Next-Gen-Eng-Apps/Develop/Sprint%20103
PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description | Team
21003 | Run newly created FR215 check with existing result validation script | 36032 | Task | Run newly created FR215 check with existing result validation script | John Streckfuss II | To Do |  | 2 |  | QA / Testing |  |  | Foundation
31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch | Foundation
34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11 |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14 |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing |  |  | Foundation
34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14 |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14 |  | Foundation
34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03 |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing |  |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14 |  | Foundation
34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02 |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04 |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development |  |  | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions() | Foundation
34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed. | Foundation
34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
34791 | Complete Transverse Detail Logging Framework | [11 empty] | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing |  |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14 |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing |  |  | Foundation
35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03 |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing |  |  | Foundation
35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing |  |  | Foundation
35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35320 | TBHD result verification - Panamax Manual Fr60 | 36036 | Task | TBHD result verification - Panamax Manual Fr60 | John Streckfuss II | In Progress |  | 4 | 3 | Development |  |  | Foundation
35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf. | Foundation
35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | Foundation
35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development |  |  | Foundation
35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development |  |  | Foundation
35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development |  |  | Foundation
35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing |  |  | Foundation
35650 | Create RuleSet for FPSO ReassessedScantling | [11 empty] | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData() | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09 |  | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list | Foundation
35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | Foundation
35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14 |  | Foundation
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14 |  | Foundation
35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14 |  | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()()) | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified. | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08 |  | Foundation
35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11 |  | Foundation
35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke | Foundation
35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | In Progress |  | 4 | 2 | Development |  | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts | Foundation
35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01 |  | Foundation
35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | Foundation
35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02 |  | Foundation
35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03 |  | Foundation
35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10 |  | Foundation
35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10 |  | Foundation
35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression | Foundation
35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression | Foundation
35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results | Foundation
35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11 |  | Foundation
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36264 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. Current State Documentation | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36265 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as deisgnated by the lead developer's plans. - Planned Changes Document - Verification Document | Foundation
35900 | CorrugatedBHD Settings - Existing - Property/Method based settings. | 36266 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | Foundation
35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36267 | Task | Analyze & Research | Jon Nance | Done |  | 6 | 6 | Requirement Study | 2026-09-08 | Analyze the current state of the code, and reconcile against the lead developer's plans to understand differences. - Current State Documentation - End State Document | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36268 | Task | Design & Plan Changes | Jon Nance | Done |  | 6 | 6 | Design / Documentation | 2026-09-08 | Plan the changes to bring the code up to modern standards and best practices, covering all points as designated by the lead developer's plans. - Planned Changes Document - Verification Document | Foundation
35903 | CorrugatedBHD Settings - Color Visitors | 36269 | Task | Review & Refactor Plans | Jon Nance | Done |  | 6 | 6 | QA / Testing | 2026-09-08 | Review the designs and planned changes with the lead developer to ensure that all goals are met, and requirements are satisfied. - Local review & testing | Foundation
35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63 | Foundation
35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 3 | Development |  |  | Foundation
35906 | Manual BC Slanted BHD Fr245 - Plate | 36026 | Task | Manual BC Slanted BHD Fr245 - Plate | John Streckfuss II | To Do |  | 8 |  | Development |  |  | Foundation
35907 | Manual BC Slanted BHD Fr245 - stiffener | 36030 | Task | Manual BC Slanted BHD Fr245 - stiffener | John Streckfuss II | To Do |  | 6 |  | Development |  |  | Foundation
35908 | Manual BC Slanted BHD Fr245 - EPP and result check | [11 empty] | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run | Foundation
35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36341 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 3 | Albert Posthauer | To Do |  | 16 | 0 | QA / Testing |  | Batch 3 - fix each one and make sure it runs | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15 |  | Foundation
35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch. | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08 |  | Foundation
35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15 |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation |  |  | Foundation
35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | In Progress |  | 4 |  | Development |  |  | Foundation
35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09 |  | Foundation
35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09 |  | Foundation
35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing |  |  | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite: | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects: | Foundation
36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes: | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos | Foundation
36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier: | Foundation
36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14 |  | Foundation
36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07 |  | Foundation
36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04 |  | Foundation
36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02 |  | Foundation
36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change | Foundation
36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15 |  | Foundation
36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab | [11 empty] | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Foundation
36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36388 | Task | Fix 2 script issues with comments run | Albert Posthauer | To Do |  | 2 |  | Development |  | Fix these from run on 9/11/26 Gap_In_The_Section_Type_28920 Input_Property_For_TBHD_Girders_Webs_28929 | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04 |  | Foundation
36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04 |  | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar, | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors: | Foundation
36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10 |  | Foundation
36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10 |  | Foundation
36377 | Draw Label in Side Frame | [11 empty] | Foundation
36378 | Draw Label in Cross Deck | [11 empty] | Foundation
36379 | Draw Label In Side Frame | [11 empty] | Foundation
36380 | GraphicTank2D Factory Refactor | 36410 | Task | spec refinement | Timothy Luna | To Do |  | 2 |  | Requirement Study |  |  | Foundation
36386 | NDepend Safety Issue - ND3106:SealMethodsThatSatisfyNonPublicInterfaces | [11 empty] | Foundation
36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these: | Foundation
36437 | Fix NDepend violation: Avoid Namespaces Mutually Dependent — HorizontalStringerBracketDimensionGeometryResolver | [11 empty] | Foundation

## CSR
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_queries/query-edit/d56ae7db-fac3-4d5c-8076-04c306b325df/
User-confirmed reporting period: 2026-09-02 to 2026-09-15
PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description | Team
35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | [11 empty] | CSR