## All
Source URL: | (combined - see individual tabs for source URLs)
Team | PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description
FPSO | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch
FPSO | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32488 | Task | TWEB Fr 89 Assessment Automation | John Streckfuss II | Done |  |  |  | Development | 2026-07-07
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35296 | Task | Regular Web Creation - SubType Filtration (Double-Side & Cargo Tank (P)/(S)/(C)) | Ricky Del Rosario | Done |  | 4 | 4 | Development | 2026-08-19
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35488 | Task | Geometry Icons - Enablement Based On Completeness of Regular Web Sub Types | Ricky Del Rosario | Done |  | 3 | 3 | Development | 2026-08-19
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35489 | Task | Vertical Web Creation Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-31
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35541 | Task | Support For Creating Bottom Transverse Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-24
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35568 | Task | Create 2 FPSO Ship Datasets (w/ & w/o inner bottom) from VLCC | Ricky Del Rosario | Done |  | 2 | 2 | Development | 2026-08-20
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35575 | Task | Without Inner Bottom - Fix the messed up outer boundary detection on new web creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-20
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35696 | Task | Test All Bracket Creation Scenarios | Ricky Del Rosario | Done |  | 4 | 4 | QA / Testing | 2026-08-26
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34958 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34959 | Task | DataModel Changes | Lokesh Gelli | Done |  | 6 | 6 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34960 | Task | View Implementation | Lokesh Gelli | Done |  | 15 | 11 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34961 | Task | View Model Implementation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34962 | Task | Smoke Test | Lokesh Gelli | Done |  | 3 | 3 | QA / Testing | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34991 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34992 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-01
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35148 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-26
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35527 | Task | Demo Task | Lokesh Gelli | Done |  | 0.5 | 0.5 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35597 | Task | PR-Review | Salina Hamal | Done |  | 2 | 2 | Design / Documentation | 2026-09-01
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35613 | Task | Code Review | Linyue Zhao | Done |  | 4 | 4 | Design / Documentation | 2026-08-31
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35745 | Task | Creation of Web Types DEFG | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35747 | Task | Brackets Creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35938 | Task | PR 13523 Rework | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-01 | PR Rejected Reason: While creating a new Trans web as per the A/c of the attached linked PBI got the Unhandled exception Error. Steps to recreate Issue: Open attached file. Navigate to ship model>Trans web> create a Trans web as per the ss Now go to Regular web> structure type cargo tank>viewpoint> and click anywhere on the graphics Notice the exception thrown
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions()
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed.
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35417 | Task | Implement Hints and Validation | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-28
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35418 | Task | Test Wave Direction | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-29
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35507 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35889 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-01
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10
FPSO | 34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34793 | Task | Create Transverse Rule Model Data | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific rule model data class that stores the TBHD hierarchy and any required parent Zone mappings so Plate/EPP/Stiffener items can be uniquely resolved internally.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34794 | Task | Create Transverse Data Manager | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific data manager that mirrors the longitudinal data manager lifecycle but operates on the transverse hierarchy and key model so that detail log data can be stored, retrieved, and managed.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34795 | Task | Create Transverse Message Handler | Peiran Li | Done |  |  | 2 | Development | 2026-09-09 | We need a transverse message handler that interprets incoming detail log messages in the context of the transverse hierarchy so that navigation, scalar updates, bulk updates, and pause/resume operations work correctly for transverse assessments.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34796 | Task | Integrate Transverse Mode into DtlLogInfoService | Peiran Li | Done |  |  | 3 | Development | 2026-09-09 | We need the main DtlLogInfoService to recognize transverse mode and wire up the correct data manager, message handler, and template so that transverse detail log sessions run end-to-end within the existing service lifecycle.
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35505 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35519 | Task | Analysis | Lokesh Gelli | Done |  | 6 | 6 | Requirement Study | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35520 | Task | Horizontal Girder Properties calculation | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35521 | Task | Vertical Web properties calculation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35522 | Task | EPP Creation for MSM | Lokesh Gelli | Done |  | 7 | 7 | Development | 2026-08-24
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35523 | Task | Stiffener Break Update on MSM | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-08-26
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35524 | Task | Validation | Lokesh Gelli | Done |  | 8 | 8 | QA / Testing | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35525 | Task | Smoke Test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35834 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-28
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35411 | Task | Add DataCategory FPSO | Gang Liu | Done |  | 2 | 2 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35412 | Task | Read FPSO | Gang Liu | Done |  | 5 | 6 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35413 | Task | Update UI of ImportView | Gang Liu | Done |  | 5 | 5 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35414 | Task | Test 3 Files | Gang Liu | Done |  | 2 | 3 | QA / Testing | 2026-08-24
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35511 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35584 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-26
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35662 | Task | Code review | Linyue Zhao | Done |  | 1 |  | Design / Documentation | 2026-08-24
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35415 | Task | Read INP FIle and so on | Gang Liu | Done |  | 6 | 7 | Development | 2026-08-26
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35416 | Task | Test Safehull | Gang Liu | Done |  | 2 | 2 | QA / Testing | 2026-08-26
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35513 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-08-31
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35782 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-28
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35783 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-08-28
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing
FPSO | 35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf.
FPSO | 35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
FPSO | 35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
FPSO | 35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development
FPSO | 35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development
FPSO | 35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing
FPSO | 35650 | Create RuleSet for FPSO ReassessedScantling | 35700 | Task | Create RuleSet for ReassessedScantling | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-08-31
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData()
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
FPSO | 35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14
FPSO | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
FPSO | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()())
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified.
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11
FPSO | 35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke
FPSO | 35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | Done |  | 4 | 2 | Development | 2026-09-15 | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts
FPSO | 35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
FPSO | 35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
FPSO | 35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10
FPSO | 35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10
FPSO | 35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression
FPSO | 35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression
FPSO | 35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results
FPSO | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35897 | Task | Internal loop investigation | Abhimanyu Kumar | In Progress |  | 8 | 6 | Requirement Study
FPSO | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11
FPSO | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring
FPSO | 35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63
FPSO | 35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 5 | Development
FPSO | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs
FPSO | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35923 | Task | Data model Changes | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36017 | Task | Update Table view and Property Panel View | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch.
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-15
FPSO | 35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09
FPSO | 35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09
FPSO | 35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite:
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects:
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes:
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier:
FPSO | 36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14
FPSO | 36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04
FPSO | 36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02
FPSO | 36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change
FPSO | 36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15
FPSO | 36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab
FPSO | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1
FPSO | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar,
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors:
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10
FPSO | 36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10
FPSO | 36377 | Draw Label in Side Frame
FPSO | 36378 | Draw Label in Cross Deck
FPSO | 36379 | Draw Label In Side Frame
FPSO | 36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these:
Foundation | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch
Foundation | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32488 | Task | TWEB Fr 89 Assessment Automation | John Streckfuss II | Done |  |  |  | Development | 2026-07-07
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35296 | Task | Regular Web Creation - SubType Filtration (Double-Side & Cargo Tank (P)/(S)/(C)) | Ricky Del Rosario | Done |  | 4 | 4 | Development | 2026-08-19
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35488 | Task | Geometry Icons - Enablement Based On Completeness of Regular Web Sub Types | Ricky Del Rosario | Done |  | 3 | 3 | Development | 2026-08-19
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35489 | Task | Vertical Web Creation Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-31
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35541 | Task | Support For Creating Bottom Transverse Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-24
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35568 | Task | Create 2 FPSO Ship Datasets (w/ & w/o inner bottom) from VLCC | Ricky Del Rosario | Done |  | 2 | 2 | Development | 2026-08-20
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35575 | Task | Without Inner Bottom - Fix the messed up outer boundary detection on new web creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-20
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35696 | Task | Test All Bracket Creation Scenarios | Ricky Del Rosario | Done |  | 4 | 4 | QA / Testing | 2026-08-26
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34958 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34959 | Task | DataModel Changes | Lokesh Gelli | Done |  | 6 | 6 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34960 | Task | View Implementation | Lokesh Gelli | Done |  | 15 | 11 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34961 | Task | View Model Implementation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34962 | Task | Smoke Test | Lokesh Gelli | Done |  | 3 | 3 | QA / Testing | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34991 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34992 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-01
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35148 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-26
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35527 | Task | Demo Task | Lokesh Gelli | Done |  | 0.5 | 0.5 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35597 | Task | PR-Review | Salina Hamal | Done |  | 2 | 2 | Design / Documentation | 2026-09-01
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35613 | Task | Code Review | Linyue Zhao | Done |  | 4 | 4 | Design / Documentation | 2026-08-31
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35745 | Task | Creation of Web Types DEFG | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35747 | Task | Brackets Creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35938 | Task | PR 13523 Rework | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-01 | PR Rejected Reason: While creating a new Trans web as per the A/c of the attached linked PBI got the Unhandled exception Error. Steps to recreate Issue: Open attached file. Navigate to ship model>Trans web> create a Trans web as per the ss Now go to Regular web> structure type cargo tank>viewpoint> and click anywhere on the graphics Notice the exception thrown
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions()
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed.
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35417 | Task | Implement Hints and Validation | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-28
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35418 | Task | Test Wave Direction | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-29
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35507 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35889 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-01
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10
Foundation | 34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34793 | Task | Create Transverse Rule Model Data | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific rule model data class that stores the TBHD hierarchy and any required parent Zone mappings so Plate/EPP/Stiffener items can be uniquely resolved internally.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34794 | Task | Create Transverse Data Manager | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific data manager that mirrors the longitudinal data manager lifecycle but operates on the transverse hierarchy and key model so that detail log data can be stored, retrieved, and managed.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34795 | Task | Create Transverse Message Handler | Peiran Li | Done |  |  | 2 | Development | 2026-09-09 | We need a transverse message handler that interprets incoming detail log messages in the context of the transverse hierarchy so that navigation, scalar updates, bulk updates, and pause/resume operations work correctly for transverse assessments.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34796 | Task | Integrate Transverse Mode into DtlLogInfoService | Peiran Li | Done |  |  | 3 | Development | 2026-09-09 | We need the main DtlLogInfoService to recognize transverse mode and wire up the correct data manager, message handler, and template so that transverse detail log sessions run end-to-end within the existing service lifecycle.
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35505 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35519 | Task | Analysis | Lokesh Gelli | Done |  | 6 | 6 | Requirement Study | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35520 | Task | Horizontal Girder Properties calculation | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35521 | Task | Vertical Web properties calculation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35522 | Task | EPP Creation for MSM | Lokesh Gelli | Done |  | 7 | 7 | Development | 2026-08-24
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35523 | Task | Stiffener Break Update on MSM | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-08-26
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35524 | Task | Validation | Lokesh Gelli | Done |  | 8 | 8 | QA / Testing | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35525 | Task | Smoke Test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35834 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-28
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35411 | Task | Add DataCategory FPSO | Gang Liu | Done |  | 2 | 2 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35412 | Task | Read FPSO | Gang Liu | Done |  | 5 | 6 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35413 | Task | Update UI of ImportView | Gang Liu | Done |  | 5 | 5 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35414 | Task | Test 3 Files | Gang Liu | Done |  | 2 | 3 | QA / Testing | 2026-08-24
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35511 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35584 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-26
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35662 | Task | Code review | Linyue Zhao | Done |  | 1 |  | Design / Documentation | 2026-08-24
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35415 | Task | Read INP FIle and so on | Gang Liu | Done |  | 6 | 7 | Development | 2026-08-26
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35416 | Task | Test Safehull | Gang Liu | Done |  | 2 | 2 | QA / Testing | 2026-08-26
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35513 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-08-31
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35782 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-28
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35783 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-08-28
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing
Foundation | 35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf.
Foundation | 35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
Foundation | 35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
Foundation | 35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development
Foundation | 35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development
Foundation | 35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing
Foundation | 35650 | Create RuleSet for FPSO ReassessedScantling | 35700 | Task | Create RuleSet for ReassessedScantling | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-08-31
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData()
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
Foundation | 35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14
Foundation | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
Foundation | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()())
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified.
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11
Foundation | 35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke
Foundation | 35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | Done |  | 4 | 2 | Development | 2026-09-15 | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts
Foundation | 35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
Foundation | 35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
Foundation | 35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10
Foundation | 35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10
Foundation | 35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression
Foundation | 35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression
Foundation | 35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results
Foundation | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35897 | Task | Internal loop investigation | Abhimanyu Kumar | In Progress |  | 8 | 6 | Requirement Study
Foundation | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11
Foundation | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring
Foundation | 35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63
Foundation | 35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 5 | Development
Foundation | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs
Foundation | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35923 | Task | Data model Changes | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36017 | Task | Update Table view and Property Panel View | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch.
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-15
Foundation | 35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09
Foundation | 35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09
Foundation | 35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite:
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects:
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes:
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier:
Foundation | 36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14
Foundation | 36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04
Foundation | 36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02
Foundation | 36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change
Foundation | 36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15
Foundation | 36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab
Foundation | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1
Foundation | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar,
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors:
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10
Foundation | 36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10
Foundation | 36377 | Draw Label in Side Frame
Foundation | 36378 | Draw Label in Cross Deck
Foundation | 36379 | Draw Label In Side Frame
Foundation | 36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these:
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35830 | Task | TBHD Rpt : Replace CSR IDs with Unified IDs in diagrams for PLATES of all tbhd structures | Mithun Banerjee | Done |  |  | 8 | Development | 2026-09-01
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35831 | Task | TBHD Rpt : Replace CSR IDs with Unified IDs in diagrams for STIFFENERS of all tbhd structures | Mithun Banerjee | Done |  |  | 8 | Development | 2026-09-01
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35832 | Task | TBHD Rpt : Diagrams for plates and stiffeners are too small to be legible | Mithun Banerjee | Done |  |  | 12 | Development | 2026-09-01 | The graphic for plates and stiffeners is unreadable due to its small size, needs better framing and scaling to inprove legibility. Even after zooming, it becomes more vague and more unreadable.
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 36137 | Task | PR Rework | Salina Hamal | Deferred |  |  |  | Development

## FPSO
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_sprints/backlog/Unified%20FPSO/Next-Gen-Eng-Apps/Develop/Sprint%20103
Team | PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description
FPSO | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch
FPSO | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32488 | Task | TWEB Fr 89 Assessment Automation | John Streckfuss II | Done |  |  |  | Development | 2026-07-07
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing
FPSO | 34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35296 | Task | Regular Web Creation - SubType Filtration (Double-Side & Cargo Tank (P)/(S)/(C)) | Ricky Del Rosario | Done |  | 4 | 4 | Development | 2026-08-19
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35488 | Task | Geometry Icons - Enablement Based On Completeness of Regular Web Sub Types | Ricky Del Rosario | Done |  | 3 | 3 | Development | 2026-08-19
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35489 | Task | Vertical Web Creation Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-31
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35541 | Task | Support For Creating Bottom Transverse Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-24
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35568 | Task | Create 2 FPSO Ship Datasets (w/ & w/o inner bottom) from VLCC | Ricky Del Rosario | Done |  | 2 | 2 | Development | 2026-08-20
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35575 | Task | Without Inner Bottom - Fix the messed up outer boundary detection on new web creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-20
FPSO | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35696 | Task | Test All Bracket Creation Scenarios | Ricky Del Rosario | Done |  | 4 | 4 | QA / Testing | 2026-08-26
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34958 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34959 | Task | DataModel Changes | Lokesh Gelli | Done |  | 6 | 6 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34960 | Task | View Implementation | Lokesh Gelli | Done |  | 15 | 11 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34961 | Task | View Model Implementation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34962 | Task | Smoke Test | Lokesh Gelli | Done |  | 3 | 3 | QA / Testing | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34991 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34992 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-01
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35148 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-26
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35527 | Task | Demo Task | Lokesh Gelli | Done |  | 0.5 | 0.5 | Development | 2026-08-20
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35597 | Task | PR-Review | Salina Hamal | Done |  | 2 | 2 | Design / Documentation | 2026-09-01
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35613 | Task | Code Review | Linyue Zhao | Done |  | 4 | 4 | Design / Documentation | 2026-08-31
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35745 | Task | Creation of Web Types DEFG | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35747 | Task | Brackets Creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing
FPSO | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35938 | Task | PR 13523 Rework | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-01 | PR Rejected Reason: While creating a new Trans web as per the A/c of the attached linked PBI got the Unhandled exception Error. Steps to recreate Issue: Open attached file. Navigate to ship model>Trans web> create a Trans web as per the ss Now go to Regular web> structure type cargo tank>viewpoint> and click anywhere on the graphics Notice the exception thrown
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions()
FPSO | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed.
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35417 | Task | Implement Hints and Validation | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-28
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35418 | Task | Test Wave Direction | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-29
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35507 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35889 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-01
FPSO | 34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10
FPSO | 34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34793 | Task | Create Transverse Rule Model Data | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific rule model data class that stores the TBHD hierarchy and any required parent Zone mappings so Plate/EPP/Stiffener items can be uniquely resolved internally.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34794 | Task | Create Transverse Data Manager | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific data manager that mirrors the longitudinal data manager lifecycle but operates on the transverse hierarchy and key model so that detail log data can be stored, retrieved, and managed.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34795 | Task | Create Transverse Message Handler | Peiran Li | Done |  |  | 2 | Development | 2026-09-09 | We need a transverse message handler that interprets incoming detail log messages in the context of the transverse hierarchy so that navigation, scalar updates, bulk updates, and pause/resume operations work correctly for transverse assessments.
FPSO | 34791 | Complete Transverse Detail Logging Framework | 34796 | Task | Integrate Transverse Mode into DtlLogInfoService | Peiran Li | Done |  |  | 3 | Development | 2026-09-09 | We need the main DtlLogInfoService to recognize transverse mode and wire up the correct data manager, message handler, and template so that transverse detail log sessions run end-to-end within the existing service lifecycle.
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35505 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35519 | Task | Analysis | Lokesh Gelli | Done |  | 6 | 6 | Requirement Study | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35520 | Task | Horizontal Girder Properties calculation | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35521 | Task | Vertical Web properties calculation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35522 | Task | EPP Creation for MSM | Lokesh Gelli | Done |  | 7 | 7 | Development | 2026-08-24
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35523 | Task | Stiffener Break Update on MSM | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-08-26
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35524 | Task | Validation | Lokesh Gelli | Done |  | 8 | 8 | QA / Testing | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35525 | Task | Smoke Test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-08-27
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35834 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-28
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
FPSO | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35411 | Task | Add DataCategory FPSO | Gang Liu | Done |  | 2 | 2 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35412 | Task | Read FPSO | Gang Liu | Done |  | 5 | 6 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35413 | Task | Update UI of ImportView | Gang Liu | Done |  | 5 | 5 | Development | 2026-08-20
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35414 | Task | Test 3 Files | Gang Liu | Done |  | 2 | 3 | QA / Testing | 2026-08-24
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35511 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35584 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-26
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35662 | Task | Code review | Linyue Zhao | Done |  | 1 |  | Design / Documentation | 2026-08-24
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing
FPSO | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35415 | Task | Read INP FIle and so on | Gang Liu | Done |  | 6 | 7 | Development | 2026-08-26
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35416 | Task | Test Safehull | Gang Liu | Done |  | 2 | 2 | QA / Testing | 2026-08-26
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35513 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-08-31
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35782 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-28
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35783 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-08-28
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing
FPSO | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing
FPSO | 35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf.
FPSO | 35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
FPSO | 35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
FPSO | 35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development
FPSO | 35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development
FPSO | 35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing
FPSO | 35650 | Create RuleSet for FPSO ReassessedScantling | 35700 | Task | Create RuleSet for ReassessedScantling | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-08-31
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData()
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list
FPSO | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
FPSO | 35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14
FPSO | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
FPSO | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()())
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified.
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08
FPSO | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11
FPSO | 35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke
FPSO | 35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | Done |  | 4 | 2 | Development | 2026-09-15 | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts
FPSO | 35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01
FPSO | 35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
FPSO | 35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
FPSO | 35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03
FPSO | 35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10
FPSO | 35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10
FPSO | 35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression
FPSO | 35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression
FPSO | 35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results
FPSO | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35897 | Task | Internal loop investigation | Abhimanyu Kumar | In Progress |  | 8 | 6 | Requirement Study
FPSO | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11
FPSO | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
FPSO | 35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring
FPSO | 35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63
FPSO | 35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 5 | Development
FPSO | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs
FPSO | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35923 | Task | Data model Changes | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36017 | Task | Update Table view and Property Panel View | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15
FPSO | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch.
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08
FPSO | 35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
FPSO | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-15
FPSO | 35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09
FPSO | 35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09
FPSO | 35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite:
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects:
FPSO | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes:
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos
FPSO | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier:
FPSO | 36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14
FPSO | 36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07
FPSO | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04
FPSO | 36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02
FPSO | 36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change
FPSO | 36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15
FPSO | 36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab
FPSO | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1
FPSO | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04
FPSO | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar,
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors:
FPSO | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10
FPSO | 36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10
FPSO | 36377 | Draw Label in Side Frame
FPSO | 36378 | Draw Label in Cross Deck
FPSO | 36379 | Draw Label In Side Frame
FPSO | 36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these:

## Foundation
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_sprints/backlog/Unified%20Foundation/Next-Gen-Eng-Apps/Develop/Sprint%20103
Team | PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description
Foundation | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32487 | Task | VLCC - Test Automation - Create Result verification for Imported Tweb section FR84 | John Streckfuss II | Done |  | 12 | 12 | QA / Testing | 2026-09-08 | Develop on Rajib's branch
Foundation | 31346 | VLCC - Test Automation - Create Result verification for Imported Tweb section | 32488 | Task | TWEB Fr 89 Assessment Automation | John Streckfuss II | Done |  |  |  | Development | 2026-07-07
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36079 | Task | Implement action of [Others] button | Gang Liu | Done |  | 6 | 6 | Development | 2026-09-11
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36080 | Task | Test different ship types | Gang Liu | Done |  | 6 | 6 | QA / Testing | 2026-09-14
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36087 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36088 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | In Progress |  | 1 |  | QA / Testing
Foundation | 34104 | Auto-assign Section Type by Panel Name | 36433 | Task | PR Review- QA | Salina Hamal | Done |  |  | 1 | QA / Testing | 2026-09-14
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34807 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34808 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-14
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 34886 | Task | PR Review - QA | Salina Hamal | Done |  | 3 | 3 | QA / Testing | 2026-09-15
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35296 | Task | Regular Web Creation - SubType Filtration (Double-Side & Cargo Tank (P)/(S)/(C)) | Ricky Del Rosario | Done |  | 4 | 4 | Development | 2026-08-19
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35488 | Task | Geometry Icons - Enablement Based On Completeness of Regular Web Sub Types | Ricky Del Rosario | Done |  | 3 | 3 | Development | 2026-08-19
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35489 | Task | Vertical Web Creation Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-31
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35541 | Task | Support For Creating Bottom Transverse Without Inner Bottom | Ricky Del Rosario | Done |  | 6 | 6 | Development | 2026-08-24
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35568 | Task | Create 2 FPSO Ship Datasets (w/ & w/o inner bottom) from VLCC | Ricky Del Rosario | Done |  | 2 | 2 | Development | 2026-08-20
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35575 | Task | Without Inner Bottom - Fix the messed up outer boundary detection on new web creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-20
Foundation | 34179 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - ABC | 35696 | Task | Test All Bracket Creation Scenarios | Ricky Del Rosario | Done |  | 4 | 4 | QA / Testing | 2026-08-26
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34958 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34959 | Task | DataModel Changes | Lokesh Gelli | Done |  | 6 | 6 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34960 | Task | View Implementation | Lokesh Gelli | Done |  | 15 | 11 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34961 | Task | View Model Implementation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34962 | Task | Smoke Test | Lokesh Gelli | Done |  | 3 | 3 | QA / Testing | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34991 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 34992 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-01
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35148 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-26
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35527 | Task | Demo Task | Lokesh Gelli | Done |  | 0.5 | 0.5 | Development | 2026-08-20
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35597 | Task | PR-Review | Salina Hamal | Done |  | 2 | 2 | Design / Documentation | 2026-09-01
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 35613 | Task | Code Review | Linyue Zhao | Done |  | 4 | 4 | Design / Documentation | 2026-08-31
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36025 | Bug | Corrugated BHD - Corrugated BHD Zone - Frame No. column should support Xap and X/L values. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36027 | Bug | Corrugated BHD - Geometry - Property Pane displays Ld & Bd for both Transverse & Longitudinal Orientation for Corrugated Zone. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34236 | Create Corrugated BHD - Geometry and Corrugation | 36029 | Bug | Corrugated BHD - Upper/Lower Stool - Stool Plate Property Pane does not load on the first click coming from Stool Stiffener Table. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-03
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35490 | Task | QA Integration Test | Hanumanth Sunkara | In Progress |  | 2 |  | QA / Testing
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35491 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-14
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35745 | Task | Creation of Web Types DEFG | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35747 | Task | Brackets Creation | Ricky Del Rosario | Done |  | 5 | 5 | Development | 2026-08-26
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35937 | Task | PR Review- QA | Salina Hamal | In Progress |  | 2 | 1 | QA / Testing
Foundation | 34344 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - DEFG | 35938 | Task | PR 13523 Rework | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-01 | PR Rejected Reason: While creating a new Trans web as per the A/c of the attached linked PBI got the Unhandled exception Error. Steps to recreate Issue: Open attached file. Navigate to ship model>Trans web> create a Trans web as per the ss Now go to Regular web> structure type cargo tank>viewpoint> and click anywhere on the graphics Notice the exception thrown
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36085 | Task | QA Integration Test | Hanumanth Sunkara | To Do |  | 2.5 |  | QA / Testing
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36086 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | To Do |  | 1.5 |  | QA / Testing
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36091 | Task | Create FPSO Ship Dataset Without Inner Skin and Inner Bottom | Ricky Del Rosario | Done |  | 1 | 1 | Development | 2026-09-02
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36092 | Task | Trimming of Geometries To Support Type H Web | Ricky Del Rosario | Done |  | 10 | 10 | Development | 2026-09-04
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36200 | Task | Inner Boundaries (Like Ring Opening) For Type H Web | Ricky Del Rosario | In Progress |  | 8 |  | Development
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36201 | Task | Support Bracket Creation And Update on Inner Boundaries of Type H Web | Ricky Del Rosario | To Do |  | 15 |  | Development
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36296 | Task | Refactor Complex Functions Before Redesign | Ricky Del Rosario | To Do |  | 20 | 10 | Design / Documentation |  | Candidate functions for refactoring: 1) UpdateBracketForOpening() 2) CreateBracketForOpening() 3) CreateBackingBracket() 4) ValidateAndTrimNewCargoTankOpeningCurves() 5) UpdateCargoTankOpeningBoundaryDefinitions()
Foundation | 34345 | Create Regular Web Zones for the 8 FPSO Transverse Web Types - H | 36363 | Task | AI-assisted refactoring support | Himanshu Pathak | In Progress |  |  |  | QA / Testing |  | Refactoring existing method ( UpdateBracketForOpening in TransvereWebTools.cs ) and evaluating multiple refactoring approaches in Visual Studio/Visual Studio Code. This included attempting and validating different refactoring options to identify an approach that preserved the intended behavior and was maintainable. Created AI assisted plan for refactoring and Unit test cases. Plan is executed. Executed the approved refactoring plan, using AI. Note - Ricky is main POC, I was providing AI assisted refactoring support. Summary Generated by AI I refactored UpdateBracketForOpening in TransvereWebTools.cs following TDD, exactly as planned: 1. Tests written first (against the unrefactored method), confirmed passing: UpdateBracketForOpeningTest.cs — 8 guard-clause characterization tests pinning every early-return message exactly. UpdateBracketForOpeningHelpersTest.cs — 7 tests for the extracted pure geometry helpers using synthetic points/lines. 2. Refactor: Extracted ~35 well-documented internal helper methods (visible to UnitTests.ISE via the project's existing InternalsVisibleTo ), eliminating the first/second-MSM duplication by parameterizing shared logic (while faithfully preserving genuine pre-existing divergences I discovered along the way — a differing match threshold, an inconsistent .Value unwrap, and a secondMsmFullCurve.Length() quirk reused in both MSM blocks). The orchestrator now reads as a short sequence of "resolve → call helper → check error → return" steps. 3. Verification: All 15 tests pass unchanged, both before and after refactoring. Manually tallied cyclomatic complexity (McCabe, counting boolean operators) for the orchestrator and every new helper — did three additional decomposition passes (folding the initial guard chain, the boundary-definition search loop, and the two most complex remaining helpers) until the orchestrator landed at CC ≈9 and all helpers are at or under 10. Built Eagle.Unified.GraphicEditor.csproj and UnitTests.ISE.csproj cleanly with MSBuild — no new errors/warnings introduced. Confirmed via git diff --stat that only the target file plus new test files changed.
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35417 | Task | Implement Hints and Validation | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-28
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35418 | Task | Test Wave Direction | Gang Liu | Done |  | 4 | 4 | QA / Testing | 2026-08-29
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35506 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 1.5 | QA / Testing | 2026-09-02
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35507 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-27
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35889 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-01
Foundation | 34433 | Wave Direction Factors Hints and Validation | 35890 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-09-10
Foundation | 34433 | Wave Direction Factors Hints and Validation | 36090 | Bug | Loads - Wave Direction Factors - Updating Values in the last row of Area B or D does not trigger the validation. | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 34433 | Wave Direction Factors Hints and Validation | 36093 | Bug | Loads - Wave Direction Factors - Unpinning is making the checkbox disappear for Historical/Intended Sites | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34793 | Task | Create Transverse Rule Model Data | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific rule model data class that stores the TBHD hierarchy and any required parent Zone mappings so Plate/EPP/Stiffener items can be uniquely resolved internally.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34794 | Task | Create Transverse Data Manager | Peiran Li | Done |  |  | 2 | Requirement Study | 2026-09-09 | We need a transverse-specific data manager that mirrors the longitudinal data manager lifecycle but operates on the transverse hierarchy and key model so that detail log data can be stored, retrieved, and managed.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34795 | Task | Create Transverse Message Handler | Peiran Li | Done |  |  | 2 | Development | 2026-09-09 | We need a transverse message handler that interprets incoming detail log messages in the context of the transverse hierarchy so that navigation, scalar updates, bulk updates, and pause/resume operations work correctly for transverse assessments.
Foundation | 34791 | Complete Transverse Detail Logging Framework | 34796 | Task | Integrate Transverse Mode into DtlLogInfoService | Peiran Li | Done |  |  | 3 | Development | 2026-09-09 | We need the main DtlLogInfoService to recognize transverse mode and wire up the correct data manager, message handler, and template so that transverse detail log sessions run end-to-end within the existing service lifecycle.
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35504 | Task | QA Integreation Test | Hanumanth Sunkara | Done |  | 3 | 3 | QA / Testing | 2026-09-03
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35505 | Task | QA Test Case Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35519 | Task | Analysis | Lokesh Gelli | Done |  | 6 | 6 | Requirement Study | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35520 | Task | Horizontal Girder Properties calculation | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35521 | Task | Vertical Web properties calculation | Lokesh Gelli | Done |  | 12 | 12 | Development | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35522 | Task | EPP Creation for MSM | Lokesh Gelli | Done |  | 7 | 7 | Development | 2026-08-24
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35523 | Task | Stiffener Break Update on MSM | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-08-26
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35524 | Task | Validation | Lokesh Gelli | Done |  | 8 | 8 | QA / Testing | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35525 | Task | Smoke Test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-08-27
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 35834 | Task | PR Review - QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-08-28
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36154 | Bug | Ship Model - Trans. BHD - Lower/Upper Part Length Values Stays After Bracket is Changed to Null | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36159 | Bug | Ship Model - Trans. BHD - MSM - Graphics Deselection Not Reflected in Vertical Web/Horizontal Girder Table | Hanumanth Sunkara | Done | Done | 1 | 1 | Bug Fixing | 2026-09-14
Foundation | 35008 | Populate Horizontal Girder and Vertical Web Properties Tables | 36166 | Bug | Ship Model - Trans. BHD - MSM - Upper/Lower Part Bracket Length Not Populated When Updating Start/End Brackets from Property Pane for Single or Multiple Girder/Web | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35411 | Task | Add DataCategory FPSO | Gang Liu | Done |  | 2 | 2 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35412 | Task | Read FPSO | Gang Liu | Done |  | 5 | 6 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35413 | Task | Update UI of ImportView | Gang Liu | Done |  | 5 | 5 | Development | 2026-08-20
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35414 | Task | Test 3 Files | Gang Liu | Done |  | 2 | 3 | QA / Testing | 2026-08-24
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35510 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 4.5 | QA / Testing | 2026-09-02
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35511 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-08-31
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35584 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-26
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 35662 | Task | Code review | Linyue Zhao | Done |  | 1 |  | Design / Documentation | 2026-08-24
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36099 | Bug | Import - Ship Data - After import some fields are missing data or they are do not match FPSO. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36102 | Bug | Import - Loads - The Sites are missing after import and Incorrect Loading Condition 4 value. | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 1 | Bug Fixing
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36104 | Bug | Import - Loads - Bending Moment - Bending Moment Error about Principal Particulars when leaving Bending Moment workflow | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36105 | Bug | Import - Loads - Bending Moment - The Bending Moment values are not imported at all or are incorrect. | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36107 | Bug | Import - Ship Model - 2D Compartment data does not match FPSO data | Hanumanth Sunkara | Done | Done | 2 | 3 | Bug Fixing | 2026-09-14
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36108 | Bug | Import - Ship Model - Long. Stiffener - Stiffener Position and Property Import Failure from FPSO to Unified Model | Hanumanth Sunkara | QA Ready | QA Ready | 2 | 2 | Bug Fixing
Foundation | 35270 | Import FPSO Data - From ABS Eagle FPSO | 36109 | Bug | Import - Ship Model - Plate - Plate Position Import Failure from FPSO to Unified Model | Hanumanth Sunkara | Done | Done | 2 | 1 | Bug Fixing | 2026-09-14
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35415 | Task | Read INP FIle and so on | Gang Liu | Done |  | 6 | 7 | Development | 2026-08-26
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35416 | Task | Test Safehull | Gang Liu | Done |  | 2 | 2 | QA / Testing | 2026-08-26
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35512 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 3 | 5 | QA / Testing | 2026-09-09
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35513 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 1.5 | QA / Testing | 2026-08-31
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35782 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-08-28
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35783 | Task | Code Review | Linyue Zhao | Done |  | 1 | 1 | Design / Documentation | 2026-08-28
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 35947 | Bug | When Import Cutout Library from SafeHull, .TLB should be used for selecting source file | Hanumanth Sunkara | Done | Done | 2 | 2 | Bug Fixing | 2026-09-03
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36317 | Bug | Import - Safehull - Principal Particulars - Lowest Ballast Draft Value is not imported. | Gang Liu | PR Ready | PR Ready | 1 | 1 | Bug Fixing
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36333 | Bug | Import - Safehull - Long. Member - For Plates the Thickenss and Material is not imported. | Linyue Zhao | PR Ready | PR Ready | 2 | 2 | Bug Fixing
Foundation | 35272 | Import FPSO Data - From ABS Safehull FPSO (v2.0) | 36354 | Bug | Import - Safehull - Wave Direction Factors - Loading Draft values are imported incorrectly | Linyue Zhao | PR Ready | PR Ready | 1 | 1 | Bug Fixing
Foundation | 35316 | Side Stringer 1 Geometry | 36008 | Task | Add script for Side Stringer 1 Geometry | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-02 | Add script for Side Stringer 1 Geometry based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35317 | Side Stringer 1 Plate | 36009 | Task | Add script for Side Stringer 1 Plate | Kishore Keerthi | Done |  | 5 | 5 | QA / Testing | 2026-09-03 | Add script for Side Stringer 1 Plate based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35318 | Side Stringer 1 Stf | 36010 | Task | Add script for Side Stringer 1 Stf | Kishore Keerthi | Done |  | 8 | 8 | QA / Testing | 2026-09-08 | Add script for Side Stringer 1 stiffeners based on steps provided in parent PBI. Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35560 | BUG 33825 _ regression test - Long section | 36023 | Task | BUG 33825 _ regression test - Long section | Albert Posthauer | Done |  | 6 | 8 | QA / Testing | 2026-09-03 | Continue to 35458 Validate a long section result. Such as Fr71-1400 Section check and validate EPP and Long stf table. Send to assessment and evaluate. Check result of geometry and summary for plate and stf.
Foundation | 35617 | Shcread Function addition in Unified code | 35621 | Task | Shcread Function addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
Foundation | 35618 | Functoin Dist_Factr addition in Unified code | 35622 | Task | Functoin Dist_Factr addition in Unified code | Yi Xia | To Do |  | 8 |  | Development
Foundation | 35619 | Remaining function change and overall code check | 35623 | Task | Remaining function change and overall code check | Yi Xia | To Do |  | 4 |  | Development
Foundation | 35624 | UnitTest of ShearST | 35625 | Task | Eagle FPSO sample result generation | Yi Xia | To Do |  | 6 |  | Development
Foundation | 35624 | UnitTest of ShearST | 35626 | Task | Unittest of Unified ShearST | Yi Xia | To Do |  | 8 |  | QA / Testing
Foundation | 35650 | Create RuleSet for FPSO ReassessedScantling | 35700 | Task | Create RuleSet for ReassessedScantling | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-08-31
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35857 | Task | Replace .INP file information with ScantlingGroups DTO | Abhimanyu Kumar | Done |  | 10 | 4 | Development | 2026-09-02 | Methods to replace: ReadInputFiles() RSUtil.ReadINPFile() RSUtil.ReadSHPFile() RSUtil.ReadSubPlateThickness() RSUtil.ReadStiffenerProfile() RSUtil.ReadSubPlateMaterial() RSUtil.ReadStiffenerMaterial() RSUtil.ReadStiffenerEndConnection() RSUtil.ReadStiffenerUnsupportedSpan() UpdateData()
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35858 | Task | Replace F34 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35859 | Task | Replace F35 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 6 | 6 | Development | 2026-09-09
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 35860 | Task | Replace F37 file read with Unified rule engine DTO | Abhimanyu Kumar | Done |  | 4 | 4 | Development | 2026-09-09
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36045 | Task | ReadScantlings -> Replace ReadPlateThkfromTempFile() - RSR file (from PR4) | Abhimanyu Kumar | Done |  | 6 | 8 | Development | 2026-09-04 | Reads: BetaOnsite VWBMSagging VWBMHogging TempvecPlateThk: list TempVecStfnrSM: list
Foundation | 35652 | Replace all input file reading with Unified RuleModuleInputDTO existing data structre | 36337 | Task | GetStiffenerSM | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
Foundation | 35766 | Change string "Matid" to numerical in Unified | 35994 | Task | Change string "Matid" to numerical in Unified | Abhimanyu Kumar | Done |  | 4 | 1 | Development | 2026-09-14
Foundation | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 35995 | Task | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType | Abhimanyu Kumar | Done |  | 8 | 3 | Development | 2026-09-14
Foundation | 35767 | Create new enums for reassessedScantling such as stiffenerType, stiffenerSubType and replace string comparison to enum comparison | 36001 | Task | Replace string comparison to enum comparison | Abhimanyu Kumar | Done |  | 6 | 3 | Development | 2026-09-14
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35775 | Task | Input DTO data conversion - Convert still water bending moments (SWSBM & SWHBM) for 4 sites | Shanli Tang | Done |  | 8 | 8 | Development | 2026-09-03 | Convert still water bending moments (SWSBM & SWHBM) for 4 sites
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35776 | Task | corrosion margin updates | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-03 | 1> Create function to check whether longitudinal section is single bottom. 2> Create function to get upper edge of bilge keel. 3> Pass extra parameters: isSingleBottom, upperEdgeY, serviceYear to function _queryManager.GetCorrosion() to calculate FPSO corrosion margin. 4> If SEVYR > 0, adjust corrosion margin by service year. NDCV_FAC = SEVYR/20.0 !Corrosion Margin adjustment
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35980 | Task | Input DTO data conversion - Convert beta factors | Shanli Tang | Done |  | 4 | 4 | Development | 2026-09-04 | Convert beta factors (same as Fortran reading .WXR file for ZBETA, ZBETAS. Reference function GTWXRPRJ()())
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35981 | Task | Input DTO data conversion - BLDFT: Lowest ballast water line is converted in Ship General | Shanli Tang | Done |  | 1 | 1 | Development | 2026-09-04 | Make sure BLDFT: Lowest ballast water line is converted in Ship General. But it is not correctly imported by Unified.
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 35983 | Task | Integration with GUI by setting phase flags | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-08
Foundation | 35774 | Scanlong - Integrate with GUI - For Tanker & NewBuild | 36356 | Task | Run dataset for new build | Shanli Tang | Done |  | 8 | 6 | Development | 2026-09-11
Foundation | 35789 | CSR GUI - Corrugation Seams Vertical and horizontal seams. | 36033 | Task | CSR GUI - Corrugation Seams Vertical and horizontal seams. | John Streckfuss II | Done |  | 4 | 4 | Development | 2026-09-09 | Add vertical and horizontal seams to CorrBHD Smoke
Foundation | 35790 | Smoke Script Update - Reselect Scripts and update devops pipeline - Sprint 103 | 36034 | Task | smoke scripts update | John Streckfuss II | Done |  | 4 | 2 | Development | 2026-09-15 | Add PC Import Nav Script Remove All but long member assessment Modify Execution Plan 1h Maintenance 1h Coding 1 New Script 3 altered Scripts
Foundation | 35828 | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | 36035 | Task | SwashBHD Fr63 creations and Plane Bulkhead modeling - Stiffener and Compartment | John Streckfuss II | Done |  | 6 | 6 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35955 | Task | research and write plan | Timothy Luna | Done |  | 12 | 7 | Requirement Study | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35956 | Task | Task 1: Typed settings prerequisites for the bulkhead root | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35957 | Task | Task 2: Decoration bucket on the graphic object base | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35958 | Task | Task 3: Bracket dimension geometry values and pure resolution math | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35959 | Task | Task 4: Dimension style and the atomic entity factory | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35967 | Task | Task 5: Horizontal stringer bracket geometry resolver | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-01
Foundation | 35851 | Show Bracket Size in Modeling | 35968 | Task | Task 6: Member-side dimension rendering and the render key | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
Foundation | 35851 | Show Bracket Size in Modeling | 35969 | Task | Task 7: SetMemberDimensions on the bulkhead settings | Timothy Luna | Done |  | 2 | 2 | Development | 2026-09-02
Foundation | 35851 | Show Bracket Size in Modeling | 35970 | Task | Task 8: CurrentSettings accessor on the bulkhead tool | Timothy Luna | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35972 | Task | Task 9: Horizontal Stringer Dimension grid integration | Timothy Luna | Done |  | 2 | 3 | Development | 2026-09-03
Foundation | 35851 | Show Bracket Size in Modeling | 35973 | Task | Task 10: Manual QA, then remove the temporary diagnostics | Timothy Luna | Done |  | 6 | 5 | QA / Testing | 2026-09-10
Foundation | 35851 | Show Bracket Size in Modeling | 36292 | Task | Refactor: Graphic Object owned visitor lifecycle doc | Timothy Luna | Done |  | 5 | 10 | Development | 2026-09-10
Foundation | 35854 | Implement DevOps Regression test | 36013 | Task | Understand the current CI/CD smoke pipeline | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-11 | Go through the current CI/CD smoke pipeline details Collect files needed to setup Devops pipeline for regression
Foundation | 35854 | Implement DevOps Regression test | 36014 | Task | Setup pipeline for Devops regression test | Kishore Keerthi | In Progress |  | 6 | 4 | QA / Testing |  | Establish yaml file having regression suite information Setup workstation and add it to Devops for running regression
Foundation | 35854 | Implement DevOps Regression test | 36015 | Task | Trigger test run | Kishore Keerthi | In Progress |  | 4 |  | QA / Testing |  | Trigger test runs on devops and gather results
Foundation | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35897 | Task | Internal loop investigation | Abhimanyu Kumar | In Progress |  | 8 | 6 | Requirement Study
Foundation | 35861 | ReassessedScantling Plate buckling C# code detailed review | 35898 | Task | Data structure flow | Abhimanyu Kumar | Done |  | 5 | 7 | Development | 2026-09-11
Foundation | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36011 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 1 | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35894 | Stringer 2 and 3 modeling - Manual Panamax | 36012 | Task | Add script for Stringer 2 and 3 modeling - Manual Panamax - Part 2 | Kishore Keerthi | Done |  | 4 | 6 | QA / Testing | 2026-09-09 | Add script for Side Stringer 2 and 3 based on steps provided in parent PBI. Reuse steps from 35316,35317,35318 PBIs Merge to develop, create PR and add it to execution plan in regression suite
Foundation | 35902 | SwashBHD - Stringer creation (simple) - Manual Panamax | 36037 | Task | SwashBHD - Stringer creation (simple) - Manual Panamax | John Streckfuss II | Done |  | 6 | 13 | Development | 2026-09-14 | 12 New Scripts Created 8h New Scripts 5h Maintenance and Refactoring
Foundation | 35904 | SwashBHD result verification - Manual Panamax FR63 | 36039 | Task | SwashBHD result verification - Manual Panamax | John Streckfuss II | Done |  | 6 | 1 | QA / Testing | 2026-09-03 | Add Assessment Validation for Added SwashBHD result verification - Manual Panamax FR63
Foundation | 35905 | Manual BC Slanted BHD Fr245 - geometry | 36024 | Task | Manual BC Slanted BHD Fr245 - geometry | John Streckfuss II | In Progress |  | 8 | 5 | Development
Foundation | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36047 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 1 | Albert Posthauer | Done |  | 24 | 22 | QA / Testing | 2026-09-09 | Batch 1 - fix each one and make sure it runs
Foundation | 35920 | Update and fix Regression scripts (missed to be ran) and start daily running and checking. | 36340 | Task | Update and fix Regression scripts (missed to be ran) and start daily running and checking - Batch 2 | Albert Posthauer | Done |  | 24 | 12 | QA / Testing | 2026-09-14 | Batch 2 - fix each one and make sure it runs Have to make sure it's setup on 2nd machine too and ABSTest folder updated to run
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35922 | Task | Analysis | Lokesh Gelli | Done |  | 4 | 4 | Requirement Study | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35923 | Task | Data model Changes | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35924 | Task | Calculate Effective Span | Lokesh Gelli | Done |  | 15 | 15 | Development | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 35925 | Task | Update the Existing Properties based on Flip | Lokesh Gelli | Done |  | 8 | 8 | Development | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36017 | Task | Update Table view and Property Panel View | Lokesh Gelli | Done |  | 4 | 4 | Development | 2026-09-01
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36282 | Task | test | Lokesh Gelli | Done |  | 4 | 4 | QA / Testing | 2026-09-08
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36288 | Task | QA Integration Test | Hanumanth Sunkara | Done |  | 2 | 2 | QA / Testing | 2026-09-15
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36289 | Task | QA Test Design and Test Case Creation | Hanumanth Sunkara | Done |  | 1.5 | 0.5 | QA / Testing | 2026-09-15
Foundation | 35921 | Add Flip and Buildup option for bracket for TBHD MSM and populate effective span related properties | 36336 | Task | PR Review -QA | Salina Hamal | Done |  | 2 | 2 | QA / Testing | 2026-09-15
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 35971 | Task | Create LGC Regression Test Case | Venkateswara Rao Potineni | Done |  | 8 | 8 | QA / Testing | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 35974 | Task | Generate Benchmark Data for LGC Dataset | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36044 | Task | Generate Benchmark for Container & LNG from Release2026.1 | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-02 | Resolve Null Exception Errors identified during Regression Testing Process and merge into Release2026.1 Branch. Update the Benchmark Files for both Container & LNG datasets in Develop Branch.
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36184 | Task | Update Result Output to DTOs Error Count rather than dumping all differences | Venkateswara Rao Potineni | Done |  | 2 | 2 | Development | 2026-09-08
Foundation | 35932 | LGC Regression: Create skeleton Regression Test | 36302 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35975 | Task | Generate Benchmark Data for Regression Test Comparision | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-11
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 35976 | Task | Implement LGC SpreadSheet Rule Run | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-14
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36043 | Task | Re-factor LGC Spreadsheet Execution to remove iServiceProvider Dependency | Venkateswara Rao Potineni | Done |  | 12 | 12 | Development | 2026-09-10
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36369 | Task | Implement CompareScanLongDTOs Method - Unique to LGC | Venkateswara Rao Potineni | Done |  | 6 | 6 | Development | 2026-09-11
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36409 | Task | Create Instructions/Wiki Page for adding new Dataset and generate Benchmark for MVR Regression | Venkateswara Rao Potineni | Done |  | 4 | 4 | QA / Testing | 2026-09-15
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36435 | Task | Code Review | Steve Balderrama | To Do |  |  |  | Design / Documentation
Foundation | 35933 | LGC Regression Test: Refactor Spreadsheet Service & Add Spreadsheet Rules logic and complete Regression Test | 36494 | Task | Update CompareObjects Errors with detailed information | Venkateswara Rao Potineni | Done |  | 4 | 4 | Development | 2026-09-15
Foundation | 35984 | Scanlong - Update Unit tests - | 35985 | Task | Update unit tests - remove local and move to server | Shanli Tang | Done |  | 2 | 2 | QA / Testing | 2026-09-09
Foundation | 35992 | Semcalc - Check Results | 35998 | Task | Verify results with center line BHD | Shanli Tang | Done |  | 8 | 8 | QA / Testing | 2026-09-09
Foundation | 35992 | Semcalc - Check Results | 35999 | Task | Verify results without center line BHD | Shanli Tang | To Do |  | 8 |  | QA / Testing
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36359 | Task | Update script failures for Input data scripts | Kishore Keerthi | Done |  | 2 | 2 | QA / Testing | 2026-09-10 | This is to fix Input data scripts failures of New Container Carrier test suite:
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36360 | Task | Fix scripts of CC ship modeling - Geometry Section creation | Kishore Keerthi | Done |  | 4 | 4 | Development | 2026-09-14 | This is to fix the failures of geometry section creation due to change of workflow/UI objects:
Foundation | 36000 | Update original script done for 19804 Containership Carrier Library manual modeling so that they runs on ISE develop build (PartII) | 36361 | Task | Fix scripts of CC ship modeling - Structure 1 break section type compartment | Kishore Keerthi | Done |  | 6 | 6 | Development | 2026-09-15 | This is to fix the failures of the below script due to workflow/GUI changes:
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36004 | Task | Run and analyze daily Regression results - Week 1 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-09 | For week 1 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36005 | Task | Run and analyze daily Regression results - Week 2 | Kishore Keerthi | Done |  | 4 | 4 | QA / Testing | 2026-09-15 | For week 2 of Sprint, perform the following: Ran regression suite on everyday's build from develop (and 2026.1 if time allows) Analyze the results everyday. Reported any new bugs caught in regression Updated regression scripts if GUI changes are intended. Results need to be updated here: Regression Results.xlsx
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36006 | Task | Run and analyze regression suite on specific PRs | Kishore Keerthi | Done |  | 5 | 4 | QA / Testing | 2026-09-15 | Run regression suite on requested PRs and publish results in PR comments. List of PRs updated here during sprint.: Pull request 13600: FrameView - export grids with correct Headers and 1 decimal place for Frame Interval - Repos Pull request 13675: change ABS table style behavior to include graphic update behavior. - Repos
Foundation | 36003 | Run, analyze and report results daily - Regression test suite (Sprint 103) | 36007 | Task | Rework/Maintenance on existing regression due to UI changes - Recurring bugs and others | Kishore Keerthi | Done |  | 4 | 2 | QA / Testing | 2026-09-02 | Maintenance work on regression suite based on intended changes expected. All updates on which scripts affected/changed will be done during sprint. Recurring bugs Script updates to fix latest failures due to intended changes (9/2) Pull request 13590: Adding script for Manual Panamax - Side Stringer 1 Geometry along with other updates for UI changes #PBI35316 #T36007 - Repos 1.Update table checkpoints and script for recurring bugs due to recent changes in UI: 2. Bulkhead table script for Product Carrier:
Foundation | 36038 | SPIKE - Clarification on the assessment table requirement | 36077 | Task | Review requirements and investigate current app | Gang Liu | Done |  | 6 | 6 | Requirement Study | 2026-09-14
Foundation | 36038 | SPIKE - Clarification on the assessment table requirement | 36078 | Task | Summary | Gang Liu | Done |  | 2 | 2 | Development | 2026-09-15
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36082 | Task | Fix MSB3270 related to mismatch between processor architecture warning in Eagle.CSR.Result.DataMediator | Kunal Chowdhury | Done |  | 3 | 3 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36094 | Task | Fix MC3074 warnings in code that says type does not exist in "clr-namespace..." | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36095 | Task | Fix CS0105 compiler warning that indicates a duplicate using directive | Kunal Chowdhury | Done |  | 2 | 2 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36142 | Task | Fix CS0108 warnings that says Member hides an inherited member | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36143 | Task | Suppress CS0618 warnings related to Obsolete API or member usage | Kunal Chowdhury | Done |  | 1 | 1 | Development | 2026-09-03
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36144 | Task | Analyze why warnings coming in production from tmp projects | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-07
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36145 | Task | Set warnings as errors to remaining projects | Kunal Chowdhury | Done |  | 8 | 8 | Development | 2026-09-08
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36146 | Task | Fix MVVMTKCFG0002 related to MVVM Toolkit configuration warning | Kunal Chowdhury | Done |  | 4 | 4 | Development | 2026-09-04
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36149 | Task | Fix CS0168 related to variable declared but never used | Kunal Chowdhury | Done |  | 1.5 | 4 | Development | 2026-09-07
Foundation | 36048 | Re-Evaluation of warnings cleanup - Eagle_Spectra_EA.sln (Production_Build¦Debug¦Release ¦ x64) | 36196 | Task | Enable CS1998 warning code in projects | Kunal Chowdhury | Done |  | 0.5 | 0.5 | Development | 2026-09-04
Foundation | 36110 | Track Test and Report CSR TBHD Bugs | 36111 | Task | Run Tests and Report Bugs | John Streckfuss II | Done |  | 4 | 4 | QA / Testing | 2026-09-02
Foundation | 36156 | Smoke Maintenance | 36157 | Task | Smoke Maintenance Week 1 | John Streckfuss II | Done |  | 4 | 2.5 | QA / Testing | 2026-09-04 | 9/2 : Remove TCBHD from execution Plan 9/3 : Update TransCorr BHD 9/3 : Add Visualizer for TCBHD modeling -Improves troubleshooting 9/3 Disable TCBHD Again (Regression Graphics Refactor Bug) 9/3 Update LNG 2635 and CSR Smoke Assessment for file export change
Foundation | 36156 | Smoke Maintenance | 36158 | Task | Smoke Maintenance Week 2 | John Streckfuss II | Done |  | 4 | 0 | Development | 2026-09-15
Foundation | 36170 | Ship Model - Trans. BHD - Restrict Graphic Selection by Active Tab
Foundation | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36176 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-08 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 1
Foundation | 36175 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103)) | 36177 | Task | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2 | Albert Posthauer | Done |  | 2 | 2 | QA / Testing | 2026-09-11 | Run, analyze, maintain and report results Weekly - Software Comments test suite (Sprint 103) - Week 2
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36189 | Task | Move assessment and evaluate out of main execution plan and add it below the import step so it can be enabled and disabled quickly without affecting the rest of the modeling | John Streckfuss II | Done |  | 3 | 3 | Development | 2026-09-04 | Created new assessment script for Each VLCC Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Double Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Short Hull Bulk Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Each Product Carrier Import Script, modeling and Assessment are now separate so modeling can always be run Created new assessment script for Panamax Import Script, modeling and Assessment are now separate so modeling can always be run
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36203 | Task | Add Sys.Desktop.Picture after assessment evaluate step to capture errors | John Streckfuss II | Done |  | 2 | 2 | Development | 2026-09-04
Foundation | 36188 | Break Assessment and Evaluate out of CSR import scripts so they can be enabled seperately | 36204 | Task | Split Import Test summary into Modeling and Assessment Components | John Streckfuss II | Done |  | 1.5 | 1.5 | QA / Testing | 2026-09-04
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 35988 | Task | Input DTO conversion - Convert Aft/Fwd end connection renewed info for Stiffener and Flat bar | Shanli Tang | Done |  | 2 | 2 | Development | 2026-09-09 | Convert Aft/Fwd end connection renewed info for Stiffener. Convert Aft/Fwd renewed info for flat bar,
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36294 | Task | Adjust Corrosion Margin & Cycle Based on | Shanli Tang | Done |  | 2 | 2 | Requirement Study | 2026-09-10 | 1> For Fatigue, corrosion margin adjustment is different from that for scanlong, so need to special handle. 2> Adjust Cycle in wave direction factors:
Foundation | 36286 | Fatigue - Integrate with GUI - For Tanker phase | 36325 | Task | Set flag to Tanker Phase | Shanli Tang | Done |  | 3 | 3 | Development | 2026-09-10
Foundation | 36343 | Setup all grids with graphics change notifications | 36358 | Task | PR Review - QA | Salina Hamal | Done |  | 1 | 1 | QA / Testing | 2026-09-10
Foundation | 36377 | Draw Label in Side Frame
Foundation | 36378 | Draw Label in Cross Deck
Foundation | 36379 | Draw Label In Side Frame
Foundation | 36393 | MVR maintenance and updates | 36394 | Task | MVR maintenance and updates | Albert Posthauer | In Progress |  | 6 | 8 | Development |  | Fix all these:

## CSR
Source URL: | https://dev.azure.com/abs-eagle-engineering/Next-Gen-Eng-Apps/_queries/query-edit/d56ae7db-fac3-4d5c-8076-04c306b325df/
User-confirmed reporting period: 2026-09-02 to 2026-09-15
Team | PBI ID | PBI Title | Task ID | Task Type | Task Title | Assigned To | State | Status (Board Column) | Original Estimate (hrs) | Completed Work (hrs) | Task Categorization | Done Date | Description
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35830 | Task | TBHD Rpt : Replace CSR IDs with Unified IDs in diagrams for PLATES of all tbhd structures | Mithun Banerjee | Done |  |  | 8 | Development | 2026-09-01
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35831 | Task | TBHD Rpt : Replace CSR IDs with Unified IDs in diagrams for STIFFENERS of all tbhd structures | Mithun Banerjee | Done |  |  | 8 | Development | 2026-09-01
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 35832 | Task | TBHD Rpt : Diagrams for plates and stiffeners are too small to be legible | Mithun Banerjee | Done |  |  | 12 | Development | 2026-09-01 | The graphic for plates and stiffeners is unreadable due to its small size, needs better framing and scaling to inprove legibility. Even after zooming, it becomes more vague and more unreadable.
CSR | 35605 | TBHD Report : Replace CSR IDs with Unified IDs in all GRAPHICAL STRUCTURES and DIAGRAMS for all plates and stiffeners of all tbhd structures. | 36137 | Task | PR Rework | Salina Hamal | Deferred |  |  |  | Development